## Sheet1
Designer’s Risk Register Form
Ref. | Feature, element, process or work activity e.g. construction of retaining walls, installing dry risers, constructing manholes | Description of constraints, hazards and associated risks | Designer’s interventions to eliminate or reduce risk | Significant residual risks remaining i.e. • Not obvious to a competent contractor or other designer, or • Unusual, or • Likely to be difficult to manage | Information to be provided to enable project partners to manage the risk
1 | General work on site | The site is located on a floodplain and is therefore at risk of flooding. Working near water around the restoration site. There is a risk of drowning, flooding, high velocity flows and associated hazards such as hypothermia and environmental pollution. | Specified that all works to be carried out under low flow. In river and floodplain works to stop if flooding into the floodplain and high flows in the channel / floodplain. All equipment should be moved out of the floodplain. Works schedule should be for spring /summer/autumn period when risk of flooding is reduced. Compound / plant to be located / stored outside of known flood event extents. Contractor and Sherbourne Valley Project Officer (SVPO) to be signed up to EA flood alerts- any and all track mats to be removed upon receipt of a flood alert for the area. The placement of any site compounds/welfare provisions must not cause and pollution issues. Vehicle storage/welfare facilities must not be situated immediately adjacent to the river to ensure facilities do not cause pollution issues. | Drowning. Flooding. Associated hazards such as hypothermia and environmental pollution. | Contractor to be informed of perceived residual hazards. Contractor to consider construction sequence produced for contractor’s reference. Contractor to design temporary works and put in place appropriate precautions to deal with flood risk during construction (monitor weather conditions and water levels). Works to be programmed such that no critical sections are left open at the end of the working day, or over a weekend, in case a flood event occurs.
2 | Working in vicinity of services | Service searches have been undertaken for the project. These show that the proposed works do not directly impact any of the services identified from the provided information. However, contractors should be aware of services in the locality and particularly where access routes to the site are located. Contractors should be aware of all service locations as it is possible that some may be crossed / passed under to undertake the proposed works. The contractor should set up goalposts in the vicinity of overhead lines so that machinery operators are aware of its presence. Track mats may be required across buried services. Other private services, such as land drains not already mapped, that are not picked up by utilities service searches, could be encountered during the works. This should be monitored by the contractor on site. | Service searches have been provided with the design drawings package. | Contractor to be aware of existing services location prior to undertaking the works to identify if any will be crossed or passed in order to access the site. Encountering private services, e.g. land drains that will need to be dealt with on site by the contractor with agreement by the landowner and client. | Contractor to be informed of perceived residual hazards. Location of services and control measures outlined in supplied services search. Contractor to undertake another services search prior to works.
3 | Movement of excavated soil and gravel for temporary works (e.g. gravel filled dumpy bags). | The works involve the movement of excavated soil material weighing several hundred kg. There is a risk of dropping material. | None. | Injury from falling material etc. | Contractor to be informed of perceived residual hazards. Contractor to consider construction sequence produced for contractor’s reference. Safe working zones to be established between operative and plant.
4 | Construction impact on bank stability and impact on natural processes. Activation of an active single thread channel. | The stability of the banks in the vicinity of the works of the watercourse should be monitored during the works, particularly when the bank is loaded or damaged during construction or otherwise disturbed. This is particularly the case following wet weather. The design is promoting improved local floodplain connectivity, Natural Flood Management, wetland creation and in-channel works that promote natural processes associated to an active single thread channel. This will result in wetter floodplain conditions and more frequent out of bank flows along the reinstated channel route (paleochannel of the former course of the North Brook). Improved floodplain connectivity may encourage deposition of gravels and fines within the paleochannel and floodplain, with associated low level bank erosion around deposits as they develop. This is in line with natural processes for a watercourse of this type. Wetland vegetation will develop over time in response to the reconnected palaeo channel and floodplain area. | Any signs of damage and change during and post construction should be monitored and mitigated. | Collapse of bank and fall from height. Persons being buried. Collapse / erosion of bank due to loading during works. Working with natural processes means some future changes can be unpredictable as the system stabilises over time. | Contractor to be informed of perceived residual hazards. Condition of banks and margins to be monitored during works (operatives with binoculars if required). All plant to be set back from the edge of the river. Post-project monitoring program.
5 | Construction impact on floodplain function. | The design is promoting increased wetting of the target floodplain areas through the works designed. This will result in an overall wetter local floodplain area where land use and function will need to adapt. Vegetation change will occur over time within the vicinity of the increased wetted areas and some fine sediment/gravels will likely deposit across the floodplain over time. | Any signs of channel and floodplain change during and post construction should be monitored and mitigated if deemed necessary. | Collapse of bank and fall from height. Persons being buried. Collapse / erosion of bank due to loading during works. Working with natural processes means some future changes can be unpredictable as the system stabilises over time. | Contractor to be informed of perceived residual hazards. Access route to site to be defined and all delivery drivers made aware of risks.
6 | Access to and from site. | Risk to members of public from plant movements. Access routes are to be confirmed with the client and landowner along the reach. | Public access routes closure/fencing/diversion of footpaths as required. | Injury / death from collision with vehicles. | Contractor to be informed of perceived residual hazards. Access route to site to be defined and all delivery drivers made aware of risks.
7 | Increased flood risk. | Works do not cause an increase to out of bank flooding that increases risk to property / housing or people. However, more frequent out of bank flows and minor flood extent increases under low order floods in the target floodplain, NFM and reconnection areas can be expected as part of the works. This is an objective of the overall project as these will develop into diverse wetland areas and provide NFM benefit. Temporary works (dependent on contractor approach) may partly block the floodplain reducing its capacity. If an event occurs, this could result in out of bank flows and premature flooding. Risk of flooding to adjacent land and areas adjacent to and upstream of works. | Improved connectivity to the local floodplain is an objective of the study through the proposed connection of the palaeo channel to bypass the weir on the North Brook. Recommended that contractor places a limit on height and extent of temporary works, such that if a large event occurs the temporary works will over top and not reduce channel capacity. Limit width of channel which is closed off at any one time where possible (if this is deemed required by the contractor). | Altered flood regime across the study reach. Drowning. | Contractor to be informed of perceived residual hazards. Construction to consider temporary works approach and sequence. Contractor to monitor weather forecast and river levels.
8 | Spreading of non-native species / biosecurity | Spreading of non-native species during works by moving machinery/ equipment and by boots. All plant and equipment including boots and waders to be disinfected prior to use in the river | SVPO to organise the removal of Himalayan balsam from the project area prior to the commencement of works | Increased area of non-native species. Damage, injury, death to protected species and habitats. | Comply with the Environment Agencies requirements to prevent the spread of invasive species. Contractor responsible for suitable biosecurity measures on site.
9 | Tree works | Some tree works may be required for machinery access purposes to deliver and facilitate the works, paticularly in the lowering areas. | None. | Low number of trees requiring works. Tree surveys and protected species habitat surveys to be carried out. Specialist tree work method statements are to be produced by the tree work contractor as required. | Contractor to be informed of perceived residual hazards. Site walkover to be undertaken by client with the contractor to determine any required tree works following marking out of the works. SVPPO to coordinate protected species surveys for project area prior to commencement of works.
10 | Material quantities | Increased expenditure due to minor design changes during construction based on local conditions encountered during the works (particularly anticipated volume of sediment for removal). Design is based on LiDAR and survey and volume estimates may change if there is any error in this data. Formation levels may change based on encountered ground conditions. Excavated material could be subject to expansion (dependent on type) and may initially require additional spreading area/storage volume until it compacts. Contractor should account for this in material movement costs or as part of their material management plan. | LiDAR, model data and survey information has been checked as far as possible. | Adjusted material quantities. Expansion of excavated material to be considered by contractor in their material management plan/costs. | Contractor should be made aware of associated risks and can account for them in advance.
11 | Inadequate compaction of features and use of incorrect materials results in washout of placed features. | Proposed infilling areas at risk of washout if contractor does not ensure suitable compaction. | Geomorphologist to supervise the contractor during creation and compaction of features. | None if designer’s interventions followed. | Contractor to carefully review design drawings and material requirements and to follow guidance provided by on site geomorphologist during feature creation.
12 | Works sequencing and flood risk. | A sequence of works has been provided within the accompanying Method Statement. There will be a period of time during construction where elements are part built and / or part removed. This will have implications with regards to local flood patterns, extents and timings should a flood occur when these are part constructed. This should be communicated and agreed with landowners priors to works commencing. | Works sequence provided, but risk associated to this cannot be completely removed through the design | Altered flood extents, patterns and timings during construction. | Method Statement provided with the design package.
13 | Unconsented works in the river and floodplain pre, during or post construction of the scheme. | Any unconsented works across the river and floodplain pre, during or post construction of the scheme will mean predicted impacts associated to the scheme from this study are potentially compromised and Dynamic Rivers will not be liable. | None. | Altered flood and geomorphological change across the river and floodplain as a result of any unconsented works being undertaken pre, during or post construction of the scheme. | None
14 | Fine sediment management and mitigation. | Suggestions have been made for management of fine sediment runoff and transport within the river and floodplain during construction in the Method Statement. Whilst these will help to reduce fine sediment runoff and transport downstream, these measures will not completely mitigate this issue despite best endeavours. | Fine sediment mitigation measures suggested within the Method Statement | Some fine sediment may still wash into the river despite recommended mitigation measures, particularly if large rainfall events occur or if a flood occurs across exposed soil. | Mitigation measure recommendations provided as part of the design package.
15 | Ordnance Survey Map Error | The existing 10K Ordnance Survey mapping for the site shows some minor error with regards to alignment against the LIDAR data. | Coordinates have been provided to delineate exact feature position based on available LIDAR. | Contractor to be made aware of error with regards to review of the overview drawings. | Drawings and coordinates show proposed locations of works.
16 | Excess material spreading | It has been assumed as part of the estimated costs that any excess excavated material will be stored/ spread locally outside of the active floodplain area / flood zones. | None. | Projects costs would significantly increase if material was to be transferred off site or sent to landfill. Excess material should not be spread in the active floodplain area / flood zones without agreement from the Environment Agency. | Flood extent information has been provided as part of the project reporting. Refer to Environment Agency Flood Zones.
17 | Modelling limitations linked to data | Hydraulic modelling is a simplified representation of the topographic surface with uncertainties linked to the underlying topographic data, model resolution required to produce sensible model run times and hydrological estimates used/calculated. | The models are run on the finest resolution possible and data is checked as far as is reasonably possible. | Uncertainty in hydrological estimates and any error in the underlying topographic data could produce errors in the hydraulic model outputs. | Technical note summarising the modelling undertaken.
ASSUMPTIONS - River, floodplain and water schemes that involve working with natural processes and the natural environment often means working with incomplete spatial datasets (e.g. complete utilities services coverage, current / available survey data etc). This results in risks associated to the construction phase of the project that cannot always be identified at the design stage, and it is not uncommon for unexpected issues to be encountered during construction. This often requires decisions to be made in a short timeframe on site to ensure works can continue to progress and to reduce downtime. A geomorphologist will, therefore, be providing supervision to ensure any modifications on site are appropriate in accordance with the original design and to reduce the risk of future issues arising.
Working with natural processes through river and floodplain restoration means that some changes as the system stabilises are unpredictable and not possible to quantify through the design process. A river and / or floodplain restoration scheme is often most reactive during and immediately post completion of works, with some systems taking several years to stabilise depending on climatic conditions and flood flows during that time.
1. In accordance with the Construction (Design and Management) Regulations, Regulation 9, the hazards associated with the work activity have been considered and eliminated, where possible.
2. The residual hazards and the provision made in the design solution to manage them, thus reducing the risks from the hazard, are shown below. In accordance with HSE advice only the significant hazards are recorded on this form.
3. In order to put these provisions in context, assumptions about the method of construction have been stated. However, this does not restrict the contractor to the construction methods implied by this.
4. It is understood that a competent contractor will carry out the construction, maintenance and demolition work in accordance with relevant regulations and recognised good industry practice.